## MVP1
Module | Requireds | Notes | Status | Complete percentage
Users Mangment | Login |  | Done | 100
| Users table |  | Done | 100
| Create user |  | Done | 100
| User details |  | Done | 100
| Edit user |  | Done | 100
| Permissions |  | Done | 100
Landing page | Real Estate Administation |  | Done | 100
| Add logout |  | Done | 100
| Other Administrations |  | Done | 100
Requests | Requests list |  | Done | 100
Purchase Request | Create request |  | Done | 100
| Request details |  | Done | 100
| Edit request |  | Done | 100
| Financial approval |  | Done | 100
| Offers tab |  | Done | 100
| Create offer |  | Done | 100
| Add offer Marketer |  | Done | 100
| Offer details |  | Done | 100
| Edit offer |  | Done | 100
| Add real estate owner |  | Done | 100
| Owner details |  | Done | 100
| Evaluations tab |  | Done | 100
| Create evaluation |  | Done | 100
| Evaluation details |  | Done | 100
| Edit evaluation |  | Done | 100
| Procedures tab |  | Done | 100
| Create procedure |  | Done | 100
| Request mangment |  | Done | 100
| Add the offer to bank's real estate |  | Nearly Done | 100
Rent & Rent ATM Place requests | Create request |  | Done | 100
| Request details |  | Done | 100
| Edit request |  | Done | 100
| Financial approval |  | Done | 100
| Offers tab |  | Done | 100
| Create offer |  | Done | 100
| Add offer Marketer |  | Done | 100
| Offer details |  | Done | 100
| Edit offer |  | Done | 100
| Add real estate owner |  | Done | 100
| Owner details |  | Done | 100
| Procedures tab |  | Done | 100
| Create procedure |  | Done | 100
| Request mangment |  | Done | 100
| Contract Establishment |  | Done | 100
| Add the offer to bank's real estate |  | Done | 100
Retrieval request | Create request |  | Done | 100
| Request details |  | Done | 100
| Edit request |  | Done | 100
| Evaluations tab |  | Done | 100
| Create evaluation |  | Done | 100
| Evaluation details |  | Done | 100
| Edit evaluation |  | Done | 100
| Procedures tab |  | Done | 100
| Create procedure |  | Done | 100
| Request mangment |  | Done | 100
| Add the property to bank's real estate |  | Done | 100
Other Administrations Requests | Requests list |  | Done | 100
Settings | Edit Language |  | Done | 100
Real Estate | Real estate table |  | Done | 100
| Add real estate |  | Done | 100
| Real estate details |  | Done | 100
| Edit real estate details |  | Done | 100
| Deed table |  | Done | 100
| Add deed |  | Done | 100
| Meters table |  | Done | 100
| Add meter |  | Done | 100
| Financial offers tab |  | Done | 100
| Financial offers table |  | Done | 100
| Add financial offer |  | Done | 100
| Marketers table |  | Done | 100
| Add marketer |  | Done | 100
| Evaluation tab |  | Done | 100
| Evaluations table |  | Done | 100
| Add evaluation |  | Done | 100
| Financial file |  | Done | 100
| Contract details |  | Done | 100
| Add contract |  | Done | 100
| Maintenance tab |  | Done | 100
| Add Maintenance |  | Done | 100
| Maintenance Table |  | Done | 100
Maintenance request | Create request |  | Done | 100
| Request details |  | Done | 100
| Edit request |  | Done | 100
| Offers tab |  | Done | 100
| Create offer |  | Done | 100
| Offer details |  | Done | 100
| Edit offer |  | Done | 100
| Add Maintenance Agency |  | Done | 100
| Maintenance Agency details |  | Done | 100
| Procedures tab |  | Done | 100
| Create procedure |  | Done | 100
| Request mangment |  | Done | 100
| Complete maintenance |  | Done | 100
Notification | System notifications |  | In Progress | 80
Accounting Department | Financial procedures table |  | Done | 100
| Add financial procedure |  | Done | 100
| Search for a real estate |  | Done | 100
| Financial procedure details |  | Done | 100
Total Complete Percentage |  |  |  | 99.7959

## MVP2
Module | Requireds | Notes | Status | Complete percentage
Selling Offers | Offer form |  | Completed | 100
| Offer details |  | Completed | 100
| Edit offer |  | Completed | 100
| Add counter offer |  | Completed | 100
| Counter offers table |  | Completed | 100
| Add the buyer tab |  | Completed | 100
| Add the procedure tab |  | Completed | 100
| Complete the sale |  | Completed | 100
Rent Offers | Offer form |  | Completed | 100
| Offer details |  | Completed | 100
| Edit offer |  | Completed | 100
| Add counter offer |  | Completed | 100
| Counter offers table |  | Completed | 100
| Add the Tenant tab |  | Completed | 100
| Add the procedure tab |  | Completed | 100
| Complete the rent |  | Completed | 100
Accounting Department | Update the invoices on adding payments |  |  | 0
Settings | Tax |  | Completed | 100
| Hijri Date |  | Completed | 100
Permissions | Handle all the permissions |  | Completed | 100
Real estate | Add the child real estate tab |  | Completed | 100
| Add the parent real estate |  | Completed | 100
| Add supervisor |  | Completed | 100
| Add real estate owner |  | Completed | 100
| Handle all real estate types |  | need more test | 95
| ATMs |  | need more test | 100
| Branches |  | need more test | 100
Maps | Real estate map |  | Need more test | 95
| Evaluation Map |  | Need more test | 95
| ATMs map |  | Need more test | 95
| Branches map |  | Need more test | 95
Companies Department | Clients table |  | Completed | 100
| Add Client |  | Completed | 100
| Client details |  | Completed | 100
| Update client |  | Completed | 100
Notifications | Email & Sms & system Notifications |  | Need more test | 95
Requests | Other administration purchase Request |  | Completed | 100
| Other administration rent request |  | Completed | 100
| Other administration rent ATM place request |  | Completed | 100
| Other administration retrieval request |  | Completed | 100
| Other administration maintenance request |  | Completed | 100
| Other administration real estate offers |  | Completed | 100
| Handle draft request |  | Completed | 100
Contracts | Add new contract |  | Completed | 100
| Link contract with real estate |  | Completed | 100
| Rental contracts list page |  | Completed | 100
| Rent contracts list page |  | Completed | 100
| Contract details tab |  | Completed | 100
| Contract real estats tab |  | Completed | 100
| Contract tenant tab |  | Completed | 100
| Update contract |  | Need more test | 95
| Invoice details and update |  | Need more test | 95
Jobs | Invoices jobs |  | need backend test | 85
Total Complete Percentage |  |  |  | 97.0755

## Final Product
Module | Requireds | Notes | Status | Complete percentage
Reports | Reports landing page |  | Completed | 100
| Reports chart |  | need more test | 95
| Real estate reports |  | need more test | 95
| Requests reports |  | need more test | 95
| Supervisors reports |  | need more test | 95
| Finance reports |  | need more test | 95
| Financial offers reports |  | need more test | 95
| Evaluation reports |  | need more test | 95
| Download Reports |  | need more test | 95
Total Complete Percentage |  |  |  | 95.5556

## Out of scope
Module | Requireds | Notes | Status | Complete percentage
Accounting Department | Inquiry requests table
Inquiry request
Add a query form
Financial Restrictions
Companies Restrictions
Request for payment of bills
Company Depatment | Requests
Canceled Agencies
Company Violations
Adding The Minutes Of The Meeting
Adding The Official Documents
Linking The Deposits
Reduce And Renew Contracts For Rented Real Estate Plan
Annual Evaluation | Annual Evaluation list |  |  | 0
| Select real estate evaluator |  |  | 0
| Add Evaluation |  |  | 0
| Reply on evaluation |  |  | 0
Evaluators User | Add evaluator user |  |  | 0
| Evaluators user list |  |  | 0
| Evaluator user details |  |  | 0
| Update evaluator user |  |  | 0
Users | User Deputy |  |  | 0
ATM | Add ATM to real estate |  |  | 0